        DAY6 SESSION ASSIGNMENTS (Theory)

1. How do you evaluate the performance of a project in agile?
In agile performance can be measured based on three matrics
- Velocity
- Hit Rate
- Work Remaining on Tasks
- Project Cost

velocity:velocity is predicted to first release plan based on privious inputs,then it ts compared with actuall output.
• Timeboxes actual measure of Velocity is used to predict the Velocity for subsequent Timeboxes in the Release Plan.

Hit Rate:work allocated to a Timebox that was actually completed.
• For example, if a team aimed for 100 StoryPoints of User Stories, but ended up onlycompleting 55 Story Points, their hit rate is55%.

Work Remaining on Task:
• Amount of work remaining in the task is work remaining.
• The estimate of work remaining Task will hopefully go down over time, but it may riseif the Task is more complicated thananticipated.

Project cost:
It describes the amount of cost sent on overall project. This is also a important criteria of measuring performance.Cost performance index is used to mease the cost.

If cpi>1spending less than what is expected for each story point.
If cpi<1spending more than what is expected for each story point.
If Spi>1 finish work earlier than expected.
If Spi<1 finish work later than expected.

schedule performance index:It measures the time schedules of the task and also the deliverable projects.

2. Compare traditional monitoring & control with agile monitoring & control
with respect to metrics generation?

Traditional monitoring & controling

Focus on the output of the project.
IT is concerned about observing and measuring actual performance against the plan.

changes from the plan is not acceptable unless there is change management approval.

Monitoring is observation and Control is corrective action taken as a result

- In this approach performance is measured based on factors such as cost, quality and effort.
- Cost performance index is planed to have effective utilisation of budget
- schedule performance index for proper time scheduling.
Agile monitoring & controling
- Here performance is measured through velocity.Predicting velocity for first release planing and then comparing with actual release.Focus on the outcomes thats hoew many story points are deliverable.
- Changes to plan is easly done compared to traditional.
- Performance measured in terms of
- Percentage of work allocated to a Timebox that was actually completed.
- Each day the team estimates the work remaining on each active Task.

 3. With a total project budget of $ 175,000, and having completed one out of
four Iterations, we have this product backlog and these actuals:
in our example, after Iteration 1 we should be at 25% complete)
Feature	Estimate / (storypoints)	Completed / (storypoints)	Actual Cost / dollars)
Welcome Screen	10	10	15
Advert - Splash Screen	20	20	30
Login Screen	10	10	20
Personalized Google Ads	20
Catalog Browser	20
Catalog Editor	10
Shopping Basket Browser	5
Shopping Card Editor	25$35,000
Check-out Process	20
Invoice Calculation	10
Credit Card Verification	10
PayPal Payment Handling	20
Order Confirmation Email	20
Totals	200	40	65

Solution:
        Given :Total project budget of $ 175,000.
        25% of task is completed.
Baseline velocity=Total project buget BAC*Total project completed
        =$175000*(25/100)
        =$43,750
completed value =completed story points/Total estimated storypoints
        = 40/200
        =20%
Earned valued = (20/100)*$175000
        =$35,000